## גיליון1
Bug ID | Date | Version | Reference | Bug Describtion | Steps | Status | Severity | Priority | Detected By | Fixed By | Date Closed
1 | 2022-03-20 | 4 | TC-003 | The describtion of products is not suitable for the products (It's wrong) | 1.Navigate to site 2.Press Store button/Shop Now button 3.Select a product | New | Medium | High | Ayah Khalilieh | Developer Name
2 | 2022-03-20 | 4 | TC-005 | Price in wrong currency | 1.Navigate to site 2.Press Store button/Shop Now button 3. Select a product | New | Medium | High | Ayah Khalilieh | Developer Name
3 | 2022-03-20 | 4 | TC-012 | I's not available for users to create a new profile | 1.Navigate to site | New | High | High | Ayah Khalilieh | Developer Name
4 | 2022-03-20 | 4 | TC-013 | It's not available to log in | 1.Navigate to site | New | High | High | Ayah Khalilieh | Developer Name
5 | 2022-03-20 | 4 | TC-014 | It's not available to update profile's info | 1.Navigate to site | New | Medium | Low | Ayah Khalilieh | Developer Name
6 | 2022-03-20 | 4 | TC-015 | there is no personalized profile for users in site | 1.Navigate to site | New | Medium | Medium | Ayah Khalilieh | Developer Name
7 | 2022-03-20 | 4 | TC-016 | there is no faq in in the website | 1.Navigate to site | New | Medium | Medium | Ayah Khalilieh | Developer Name
8 | 2022-03-20 | 4 | TC-017 | there is no field for costumer to give his number in the costumer's support page | 1.Navigate to site 2.Click Contact Us link | New | Medium | Medium | Ayah Khalilieh | Developer Name
9 | 2022-03-20 | 4 | TC-018 | I's not available for users to create a new profile or log in | 1.Navigate to site | New | Low | Low | Ayah Khalilieh | Developer Name
10 | 2022-03-20 | 4 | TC-019+TC-020 | no place to select payment method thus order can't be placed | 1.Navigate to site 2.Click Store link 3.Select a product to add to cart and click it 4.Click Add To Cart button 5.Click on cart 6.Click on proceed to checkout 7.Fill in different fields in checkout page and choose shipping method | New | High | High | Ayah Khalilieh | Developer Name
11 | 2022-03-20 | 4 | TC-023 | no section for payment thus no shipping method can be selected while paying | 1.Navigate to site 2.Click Store link 3.Select a product to add to cart and click it 4.Click Add To Cart button 5.Click on cart 6.Click on proceed to checkout | New | High | High | Ayah Khalilieh | Developer Name
12 | 2022-03-20 | 4 | TC-024 | no place for user to enter order info for tracking | 1.Navigate to site | New | Medium | Medium | Ayah Khalilieh | Developer Name
13 | 2022-03-20 | 4 | TC-025 | no place to select payment method thus order can't be placed and no tax can be displayed | 1.Navigate to site 2.Click Store link 3.Select a product to add to cart and click it 4.Click Add To Cart button 5.Click on cart 6.Click on proceed to checkout 7.Fill in different fields in checkout page and choose shipping method 8.click place order button | New | Medium | High | Ayah Khalilieh | Developer Name
14 | 2022-03-20 | 4 | TC-026 | there are no available payment methods for payment | 1.Navigate to site 2.Click Store link 3.Select a product to add to cart and click it 4.Click Add To Cart button 5.Click on cart 6.Click on proceed to checkout 7.Fill in different fields in checkout page and choose shipping method 8.click place order button | New | Medium | High | Ayah Khalilieh | Developer Name
15 | 2022-03-20 | 4 | TC-027 | It's not possible for user to change orders or cancel them | 1.Navigate to site | New | Medium | Medium | Ayah Khalilieh | Developer Name
16 | 2022-03-20 | 4 | TC-029 | It's not possible for user to select a financing option | 1.Navigate to site | New | Medium | Medium | Ayah Khalilieh | Developer Name
17 | 2022-03-20 | 4 | TC-030 | there is no sitemap | 1.Navigate to site | New | Low | Medium | Ayah Khalilieh | Developer Name
18 | 2022-03-20 | 4 | TC-033 | no place to select payment method thus order can't be placed | 1.Navigate to site 2.Click Store link 3.Select a product to add to cart and click it 4.Click Add To Cart button 5.Click on cart 6.Click on proceed to checkout | New | High | High | Ayah Khalilieh | Developer Name
19 | 2022-03-26 | 4 | TC-038 | there is no multi language support | 1.Navigate to site 2.Check if site provides multi language support | New | Medium | Medium | Ayah Khalilieh | Developer Name
20 | 2022-03-26 | 4 | TC-045 | no user personal info interaction in site | 1.Navigate to Site | New | High | High | Ayah Khalilieh | Developer Name
21 | 2022-03-26 | 4 | TC-046 | there is no data storage in site | 1.Navigate to Site | New | High | High | Ayah Khalilieh | Developer Name
22 | 2022-03-26 | 4 | TC-048 | there is no guidelines/ documentation for user (for how to use site) | 1.Navigate to Site | New | Low | Medium | Ayah Khalilieh | Developer Name
23 | 2022-03-26 | 4 | TC-050 | The protocol used is HTTPS not HTTP | Check url | New | Medium | Medium | Ayah Khalilieh | Developer Name
24 | 2022-03-26 | 4 | TC-051 | site isn't on port 80 | https=port 443 | New | Medium | Medium | Ayah Khalilieh | Developer Name
25 | 2022-03-26 | 4 | TC-052 | site isn't compatible with internet explorer, design not good | 1.Navigate to site in ie | New | Low | Medium | Ayah Khalilieh | Developer Name
26 | 2022-03-26 | 4 | TC-055 | site doesn't display product warranties | 1.Navigate to Site | New | Low | Low | Ayah Khalilieh | Developer Name